## GanttChartWeek2026
Project Name |  | Office Relocation Project |  |  |  | Duration | 2026-01-01
2026-04-30
No. | Task |  | Assignee | Start Date | End Date | Progress | Status | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August | [5 empty] | September |  |  |  |  | October |  |  |  |  | November | [5 empty] | December
[8 empty] | 1 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28
[8 empty] | 1w | 2w | 3w | 4w | 5w | 6w | 7w | 8w | 9w | 10w | 11w | 12w | 13w | 14w |  | 15w | 16w | 17w | 18w |  | 19w | 20w | 21w | 22w | 23w | 24w | 25w | 26w | 27w |  | 28w | 29w | 30w | 31w |  | 32w | 33w | 34w | 35w | 36w |  | 37w | 38w | 39w | 40w |  | 41w | 42w | 43w | 44w |  | 45w | 46w | 47w | 48w | 49w |  | 50w | 51w | 52w | 53w
1 | Planning & Vendor Selection |  |  | 2026-01-01 | 2026-01-31 | 100% | Completed
2 | Define requirements |  | Alice | 2026-01-02 | 2026-01-10 | 100% | Completed
3 | Shortlist vendors |  | Bob | 2026-01-06 | 2026-01-17 | 100% | Completed
4 | Request quotations |  | Charlie | 2026-01-13 | 2026-01-24 | 100% | Completed
5 | Select contractor |  | Diana | 2026-01-20 | 2026-01-31 | 100% | Completed
6 | Interior Design & Layout |  |  | 2026-02-01 | 2026-02-28 | 80% | In Progress
7 | Create layout plan |  | Alice | 2026-02-03 | 2026-02-14 | 100% | Completed
8 | Review layout design |  | Edward | 2026-02-10 | 2026-02-21 | 75% | Delayed
9 | Finalize furniture plan |  | Bob | 2026-02-17 | 2026-02-28 | 60% | In Progress
10 | Approve final design |  | Charlie | 2026-02-24 | 2026-02-28 | 40% | In Progress
11 | IT & Infrastructure Setup |  |  | 2026-02-15 | 2026-03-31 | 60% | In Progress
12 | Network design |  | Diana | 2026-02-17 | 2026-02-28 | 20% | Delayed
13 | Server setup |  | Charlie | 2026-03-01 | 2026-03-14 | 70% | In Progress
14 | Install wiring |  | Edward | 2026-03-03 | 2026-03-21 | 40% | In Progress
15 | Security system setup |  | Bob | 2026-03-10 | 2026-03-28 | 0% | To-Do
16 | IT testing |  | Alice | 2026-03-24 | 2026-03-31 | 0% | Not Started
17 | Move Preparation |  |  | 2026-03-15 | 2026-04-15 | 45% | In Progress
18 | Create moving plan |  | Charlie | 2026-03-17 | 2026-03-28 | 60% | In Progress
19 | Pack office items |  | Diana | 2026-03-24 | 2026-04-05 | 40% | In Progress
20 | Confirm equipment list |  | Alice | 2026-03-20 | 2026-03-31 | 80% | Completed
21 | Vendor coordination |  | Edward | 2026-03-26 | 2026-04-08 | 30% | To-Do
22 | Relocation & Final Setup |  |  | 2026-04-01 | 2026-04-30 | 0% | In Progress
23 | Move furniture & equipment |  | Bob | 2026-04-02 | 2026-04-12 | 0% | Not Started
24 | Install office layout |  | Charlie | 2026-04-08 | 2026-04-18 | 0% | Not Started
25 | System configuration |  | Diana | 2026-04-10 | 2026-04-22 | 0% | Not Started
26 | Final inspection |  | Edward | 2026-04-23 | 2026-04-30 | 0% | Not Started
27
28
29
30
31
32
33
34

## Assignees
Assignee |  |  | ★ Please delete the sample data before using this sheet.
| Alice | ★Sample | ★ List the assignees in column B.
| Bob | ★Sample | ★ The background color of each assignee will be reflected in the schedule.
| Charlie | ★Sample
| Diana | ★Sample
| Edward | ★Sample

## Dates
Date |  | ★ List the dates to be used in column B.
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-01
2026-03-02
2026-03-03
2026-03-04
2026-03-05
2026-03-06
2026-03-07
2026-03-08
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-15
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-21
2026-03-22
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-29
2026-03-30
2026-03-31
2026-04-01
2026-04-02
2026-04-03
2026-04-04
2026-04-05
2026-04-06
2026-04-07
2026-04-08
2026-04-09
2026-04-10
2026-04-11
2026-04-12
2026-04-13
2026-04-14
2026-04-15
2026-04-16
2026-04-17
2026-04-18
2026-04-19
2026-04-20
2026-04-21
2026-04-22
2026-04-23
2026-04-24
2026-04-25
2026-04-26
2026-04-27
2026-04-28
2026-04-29
2026-04-30
2026-05-01
2026-05-02
2026-05-03
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-05-31
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-21
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-28
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-05
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-12
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-19
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-26
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31
2026-08-01
2026-08-02
2026-08-03
2026-08-04
2026-08-05
2026-08-06
2026-08-07
2026-08-08
2026-08-09
2026-08-10
2026-08-11
2026-08-12
2026-08-13
2026-08-14
2026-08-15
2026-08-16
2026-08-17
2026-08-18
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-23
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-30
2026-08-31
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-06
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-13
2026-09-14
2026-09-15
2026-09-16
2026-09-17
2026-09-18
2026-09-19
2026-09-20
2026-09-21
2026-09-22
2026-09-23
2026-09-24
2026-09-25
2026-09-26
2026-09-27
2026-09-28
2026-09-29
2026-09-30
2026-10-01
2026-10-02
2026-10-03
2026-10-04
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11
2026-10-12
2026-10-13
2026-10-14
2026-10-15
2026-10-16
2026-10-17
2026-10-18
2026-10-19
2026-10-20
2026-10-21
2026-10-22
2026-10-23
2026-10-24
2026-10-25
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-08
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-15
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-22
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-29
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-06
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-13
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-20
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-25
2026-12-26
2026-12-27
2026-12-28
2026-12-29
2026-12-30
2026-12-31

## Progress
Progress (%) |  | ★ List progress values (0%–100%) in column B.
| 0% | ★ These values can be used for the “Progress (%)” field in the schedule.
5%
10%
15%
20%
25%
30%
35%
40%
45%
50%
55%
60%
65%
70%
75%
80%
85%
90%
95%
100%

## Status
Status |  | ★ List the status options in column B.
| Not Started | ★ Each status color will be reflected in the schedule.
To-Do
In Progress
Delayed
Completed